# Smart Campus Energy Management System

# Project Meeting Notes and Progress Reports

## Document Version: 1.0

Last Updated: November 20, 2025

Project Name: Smart Campus Energy Management System Report Prepared By: Kayode Babalola, Qianru Deng, Priyanka Sharma (Project Manager)

Project Team: Kayode Babalola, Qianru Deng, Priyanka Sharma Organization: St. Clair College

# Document Overview

This document contains comprehensive meeting notes and progress reports for the Smart Campus Energy Management System project. It includes detailed status updates, risk assessments, budget tracking, and team performance metrics from September 2025 through November 2025.

# Meeting Notes - November 13, 2025

Meeting Type: Weekly Project Status Review

Date: November 13, 2025

Time: 1:30 PM - 2:00 PM EST

Location: Zoom Video Conference

## Attendees:

Priyanka Sharma (Project Manager) Kayode Babalola (Product Manager) Qianru Deng (Technical Lead)

# Agenda Items

- Project Status Update Across All Workstreams

- Risk Identification and Mitigation Strategies

- Budget Review and Financial Status

- Deliverables Review and Timeline

- Action Items Assignment

- Next Steps and Upcoming Milestones

# Project Status Update

Current Project Phase: Active Implementation (Week 8 of 16-week project timeline)

Overall Project Health: ON TRACK ✅

# Project Initiation - COMPLETE

Completion Date: October 5, 2025

## Key Achievements:

Comprehensive stakeholder identification and mapping completed Project scope, objectives, and success criteria finalized

Team roles, responsibilities, and reporting structure established Project Charter approved by all stakeholders

Initial risk assessment completed

## Deliverables:

Project Charter (version 2.0 with stakeholder approval) Stakeholder Communication Plan

Project Governance Framework

# Energy Audit - IN PROGRESS (85% Complete)

Current Status: Nearing completion, slightly behind schedule

## Progress Details:

Completed comprehensive energy audit of 8 out of 10 major campus buildings

Remaining 2 buildings (Library and Student Center) scheduled for completion by November 25 Energy consumption baseline successfully established: 2,450 kWh/day average across campus Peak consumption identified: 3,200 kWh during winter months

High-consumption areas mapped for priority optimization

## Key Findings:

Engineering Building accounts for 28% of total campus energy consumption HVAC systems represent 45% of building energy use

Lighting systems represent 22% of building energy use

Significant energy waste identified during unoccupied hours (15-20% potential savings)

Team Member Responsible: Kayode Babalola

# Sensor Procurement - COMPLETE

Completion Date: November 8, 2025

## Progress Details:

Successfully ordered and received 28 energy monitoring sensors Model: Smart Energy Meter (SEM-3000) from TechSensor Inc.

All sensors passed quality inspection and acceptance testing Sensors are calibrated and ready for campus-wide installation Sensor documentation and manuals distributed to installation team

Budget Performance: Completed $2,500 under budget due to volume discount

Team Member Responsible: Qianru Deng

# Sensor Installation - IN PROGRESS (40% Complete)

Current Status: On track with minor weather-related delays

## Progress Details:

Installation completed in 3 buildings (Engineering, Business, Health Sciences) 11 sensors successfully deployed and transmitting data

Remaining 7 buildings scheduled for installation: November 22 - December 1 Installation schedule coordinated with facilities management to minimize disruption Weather delays anticipated mid-week due to forecasted rain

## Installation Sites Remaining:

Library (3 sensors) Student Center (4 sensors)

Science Building (4 sensors) Arts Building (2 sensors) Athletics Center (3 sensors) Residence Hall A (2 sensors) Cafeteria (1 sensor)

Team Member Responsible: Kayode Babalola (coordination), Qianru Deng (technical oversight)

# Dashboard Development - IN PROGRESS (60% Complete)

Current Status: On track for November 28 completion

## Progress Details:

Backend API development 70% complete Database schema finalized and deployed

API endpoints for data retrieval implemented and tested Frontend UI screens designed and approved by stakeholders Data visualization components 50% implemented

Integration testing scheduled to begin November 25

## Technical Stack:

Backend: Python/Django REST Framework Frontend: React.js with Material-UI Database: PostgreSQL

Cloud Platform: AWS

Team Member Responsible: Qianru Deng

# Data Analysis and Modeling - IN PROGRESS (50% Complete)

Current Status: On track with preliminary results

## Progress Details:

Historical energy data collection from facilities management completed Data cleaning and normalization processes implemented

Preliminary consumption pattern analysis completed Machine learning prediction model development underway Initial model accuracy: 82% (target: 85%)

Time-series analysis revealing daily and weekly patterns

## Key Insights:

Energy consumption peaks: Monday-Wednesday 10 AM - 2 PM Weekend consumption 40% lower than weekdays

Seasonal variations: Winter +25%, Summer +15% vs. Spring/Fall baseline

Team Member Responsible: Kayode Babalola

# Risks Identified and Mitigation Strategies

  - High Priority Risk

Risk #1: Sensor Installation Delays Due to Weather Conditions

| Category | amp; Details |
| --- | --- |
| Probability Impact Description Mitigation Strategy Contingency Plan Owner Status | amp; High (70% chance of impact) amp; Medium (could delay dashboard launch by 5-7 days) amp; Recent weather forecasts indicate rain and potential snow in late November, which may impact outdoor sensor installation work amp; (1) Prioritize indoor sensor installations first; (2) Increase installation crew size from 2 to 4 personnel; (3) Schedule alternative installation dates; (4) Coordinate with facilities for indoor workspace access amp; If delays exceed 7 days, launch dashboard with partial sensor coverage (minimum 20 sensors) and complete remaining installations post- launch amp; Kayode Babalola amp; Active monitoring, mitigation in progress |

# Budget Update and Financial Status

| Budget Category | amp; Allocated | amp; Spent | amp; Remaining | amp; % Utilized |
| --- | --- | --- | --- | --- |
| Labor (Team Hours) | amp; $214,000 | amp; $156,000 | amp; $58,000 | amp; 72.9% |
| Equipment (Sensors &amp; Networking) | amp; $67,500 | amp; $65,000 | amp; $2,500 | amp; 96.3% |
| Software &amp; Cloud Services | amp; $20,000 | amp; $12,000 | amp; $8,000 | amp; 60.0% |
| Training &amp; Development | amp; $5,000 | amp; $1,500 | amp; $3,500 | amp; 30.0% |
| Contingency Reserve (5%) | amp; $15,325 | amp; $0 | amp; $15,325 | amp; 0.0% |
| Total Project Budget | amp; $321,825 | amp; $234,500 | amp; $87,325 | amp; 72.9% |

Financial Status: ON TRACK ✅

## Budget Analysis:

Project is 72.9% complete in spending with 73% of timeline elapsed

Equipment procurement completed under budget due to volume discount negotiation Software and cloud costs lower than expected due to educational pricing

Training budget largely unspent (scheduled for late November)

Contingency reserve ($15,325) remains intact and available for unforeseen issues Projected final cost: $318,000 (3.8% under budget)

## Cost Savings Achieved:

Sensor procurement: $2,500 savings from volume discount

Cloud services: $3,000 annual savings through AWS education program Software licenses: $2,500 savings through academic partnerships

# Deliverables Review

  - Completed Deliverables

## Project Charter (Version 2.0)

Approved: October 15, 2025

Includes stakeholder signatures and change log  Status: Archived in project repository

## Energy Audit Report (Draft)

Completed: November 10, 2025 (8 buildings)

Contains baseline consumption data and analysis

Status: Under review; final version due November 25

## Sensor Specifications and Procurement Documentation

Completed: November 8, 2025

Includes vendor contracts, technical specs, and acceptance testing results  Status: Filed and archived

# In-Progress Deliverables

## Dashboard Prototype (Backend + Frontend)

Expected Completion: November 28, 2025

Current Progress: 60%

Status: Development on schedule

## GitHub Repository with Project Codebase

Expected Completion: November 30, 2025 (Version 1.0)

Current Progress: 75%

Status: Regular commits ongoing (3 versions planned)

## Educational Campaign Materials

Expected Completion: November 30, 2025

Current Progress: 45%

Status: Content creation in progress

# Upcoming Deliverables

## Final Deployment Guide and User Documentation

Due Date: December 1, 2025  Assigned To: Qianru Deng

Status: Outline complete, writing phase pending

## User Training Materials (Videos + Manuals)

Due Date: November 30, 2025  Assigned To: Priyanka Sharma  Status: Planning phase

## Launch Campaign Materials and Communication Plan

Due Date: December 1, 2025  Assigned To: Kayode Babalola  Status: Draft phase

# Action Items and Responsibilities

| Action Item | amp; Owner | amp; Due Date | amp; Status |
| --- | --- | --- | --- |
| Complete sensor installation in remaining 7 buildings | amp; Kayode Babalola | amp; Dec 1, 2025 | amp; In Progress |
| Finalize dashboard UI and complete integration testing | amp; Qianru Deng | amp; Nov 28, 2025 | amp; On Track |
| Prepare comprehensive user training materials (videos + guides) | amp; Priyanka Sharma | amp; Nov 30, 2025 | amp; Not Started |
| Conduct user acceptance testing with 50- person test group | amp; All Team Members | amp; Dec 1, 2025 | amp; Pending |
| Final project documentation review and submission | amp; Priyanka Sharma | amp; Dec 2, 2025 | amp; Pending |
| Coordinate with IT department for system integration | amp; Qianru Deng | amp; Nov 25, 2025 | amp; In Progress |
| Develop launch communication strategy and materials | amp; Kayode Babalola | amp; Nov 30, 2025 | amp; In Progress |

- Next Steps and Upcoming Milestones

## Immediate Next Steps (Next 7 Days):

- Schedule Mid-Project Stakeholder Review Meeting

Proposed Date: November 22, 2025

Purpose: Present progress, address concerns, obtain feedback  Attendees: Project team, supervisor, key stakeholders

## Conduct Technical Integration Testing

Scheduled: November 25-27, 2025

Focus: Sensor-to-dashboard data flow, API functionality, user authentication  Team: Qianru Deng (lead) with full team support

## Finalize Educational Campaign Messaging

Deadline: November 23, 2025

Deliverable: Campaign taglines, messaging framework, visual assets  Owner: Kayode Babalola

## Prepare for Final Deliverable Submission

Target: December 1, 2025

Activities: Documentation review, quality assurance, final testing  Owner: Priyanka Sharma (coordination)

## Critical Milestones Ahead:

November 22: Mid-project stakeholder review November 25: Integration testing begins November 28: Dashboard prototype completion November 30: Training materials finalized December 1: Final project delivery and launch

Next Regular Team Meeting: November 22, 2025 at 1:00 PM EST

Meeting Adjourned: 2:00 PM EST

# Monthly Progress Report - November 2025

Reporting Period: November 1-20, 2025

Project Phase: Implementation Phase (Weeks 6-8 of 16-week timeline)

Report Date: November 20, 2025

Prepared By: Priyanka Sharma, Project Manager

# Executive Summary

The Smart Campus Energy Management System project continues to progress successfully toward its December 1, 2025 delivery deadline. During the November reporting period, the team achieved significant milestones including completion of sensor procurement, advancement of the energy audit to 85%, and substantial progress on dashboard development (60% complete). The project remains on track both in terms of timeline and budget, with 72.9% of funds utilized and 73% of project duration elapsed.

Two minor challenges emerged during this period: weather-related delays in sensor installation and third-party integration requirements from campus IT. Both issues have been addressed through proactive mitigation strategies, and the project timeline remains intact. Team collaboration continues to be strong, with all members contributing effectively to their assigned responsibilities.

With 11 days remaining until the final delivery date, the team is focused on completing sensor installations, finalizing the dashboard prototype, and preparing comprehensive training materials. All indicators suggest successful project completion on schedule and within budget.

# Key Performance Metrics

| Metric | amp; Target | amp; Actual | amp; Status |
| --- | --- | --- | --- |
| Overall Project Completion | amp; 50% | amp; 52% | amp; On Track ✅ |
| Energy Audit Completion | amp; 100% | amp; 85% | amp; Slightly Behind ⚠ |
| Sensor Installation Progress | amp; 50% | amp; 40% | amp; On Track ✅ |
| Dashboard Development | amp; 60% | amp; 60% | amp; On Track ✅ |
| Data Analysis &amp; Modeling | amp; 50% | amp; 50% | amp; On Track ✅ |
| Budget Utilization | amp; 75% | amp; 72.9% | amp; Within Range ✅ |
| Team Satisfaction | amp; 80%+ | amp; 85% | amp; Excellent ✅ |
| Stakeholder Engagement | amp; High | amp; High | amp; Excellent ✅ |

Overall Project Health: ON TRACK ✅

# Achievements and Milestones This Period

- Energy Audit Advancement

Achievement: Completed detailed energy consumption analysis for 8 out of 10 major campus buildings

## Key Results:

Established comprehensive energy baseline: 2,450 kWh/day average campus-wide Identified peak consumption periods: Monday-Wednesday, 10 AM - 2 PM

Mapped high-consumption areas: Engineering Building (28% of total), HVAC systems (45% of building usage) Documented 15-20% potential energy savings during unoccupied hours

Created detailed consumption profiles for each audited building

Impact: Provides critical data foundation for optimization recommendations and ROI projections

# Sensor Network Procurement and Deployment Progress

Achievement: All 28 energy monitoring sensors procured, inspected, and 11 sensors successfully deployed

## Key Results:

Completed vendor selection and procurement process ahead of schedule Negotiated volume discount saving $2,500 in equipment costs

All sensors passed quality inspection and acceptance testing

Successfully installed and activated sensors in 3 buildings (Engineering, Business, Health Sciences) Sensors transmitting data reliably with 99.2% uptime

Established installation framework and procedures for remaining buildings

Impact: Demonstrates technical feasibility and builds momentum for full campus deployment

# Dashboard Development Milestone

Achievement: 60% completion of integrated dashboard platform (backend + frontend)

## Key Results:

Backend API architecture designed, implemented, and 70% tested Database schema finalized with support for real-time and historical data RESTful API endpoints created for all major data operations

Frontend UI design completed and approved by stakeholders

Data visualization components implemented (charts, graphs, heat maps) User authentication and authorization system functional

Impact: On track for November 28 prototype completion, enabling user acceptance testing

# Team Performance and Collaboration

Achievement: Strong team cohesion with effective cross-functional collaboration

## Key Results:

100% attendance at weekly team meetings

Zero major interpersonal conflicts or communication issues Collaborative problem-solving on technical integration challenges

Mutual support across team members when workload spikes occurred Regular knowledge sharing sessions enhancing team capabilities

Impact: Positive team dynamics contribute to productivity and project success

# Challenges, Issues, and Resolutions

Challenge 1: Weather-Related Installation Delays

## Description:

Recent rainy weather conditions in mid-November delayed outdoor sensor installation activities. Installation crew unable to work safely on exterior building locations during wet conditions.

## Impact:

5 days behind on sensor installation schedule

Risk of cascading delays to dashboard integration testing Potential impact on December 1 launch date

## Resolution Implemented:

  - Prioritized indoor sensor installations to maintain progress

  - Increased installation crew from 2 to 4 personnel to accelerate work

  - Scheduled alternative installation dates during forecasted dry weather

  - Coordinated with facilities management for extended access to indoor locations

  - Revised installation schedule with buffer time built in

Current Status: ✅ RESOLVED

Installation back on track with new accelerated schedule. No impact expected on project deadline.

# Challenge 2: Third-Party Integration Security Requirements

## Description:

Campus IT department requested additional security protocols and authentication measures beyond initial specifications. Required enhanced data encryption and multi-factor authentication for admin accounts.

## Impact:

3-day delay in system integration timeline

Additional development work required for security enhancements Slight budget impact for security consulting ($1,200)

## Resolution Implemented:

- Conducted emergency meeting with IT security team to understand requirements

- Implemented enhanced TLS 1.3 encryption for all data transmission

- Integrated multi-factor authentication (MFA) for administrator access

- Conducted security audit and penetration testing

- Updated technical documentation with new security protocols

Current Status: ✅ RESOLVED

All security requirements met and approved by IT department. Integration testing proceeding as scheduled.

# Financial Status and Budget Analysis

| Category | amp; Budget | amp; Spent | amp; Remaining | amp; Variance |
| --- | --- | --- | --- | --- |
| Labor | amp; $214,000 | amp; $156,000 | amp; $58,000 | amp; +$0 |
| Equipment | amp; $67,500 | amp; $65,000 | amp; $2,500 | amp; +$2,500 |
| Software | amp; $20,000 | amp; $12,000 | amp; $8,000 | amp; +$8,000 |
| Training | amp; $5,000 | amp; $1,500 | amp; $3,500 | amp; +$3,500 |
| Security Consulting | amp; $0 | amp; $1,200 | amp; -$1,200 | amp; -$1,200 |
| Contingency | amp; $15,325 | amp; $0 | amp; $15,325 | amp; +$15,325 |
| Total | amp; $321,825 | amp; $234,500 | amp; $87,325 | amp; +$3,800 |

Total Budget: $321,825

Spent to Date: $234,500 (72.9% utilized) Remaining Budget: $87,325 (27.1%) Projected Final Cost: $318,000

Projected Savings: $3,825 (1.2% under budget)

## Financial Analysis:

The project maintains healthy financial status with expenditures closely aligned to project timeline progress. Key financial highlights:

Equipment savings: $2,500 under budget due to volume discount negotiation

Software savings: $8,000 under budget through AWS education program and academic software licenses

Contingency fund: $15,325 untouched and available for any final-phase issues

Minor overage: $1,200 unplanned security consulting expense (absorbed by software savings)

Projection: Expected to complete project $3,825 under original budget (1.2% savings)

Budget Risk Assessment: LOW RISK

Sufficient funds available for remaining activities with contingency buffer intact.

# Team Productivity and Performance

| Team Member | amp; Assigned | amp; Completed | amp; In Progress | amp; Performance |
| --- | --- | --- | --- | --- |
| Priyanka Sharma Kayode Babalola Qianru Deng | amp; 18 amp; 15 amp; 16 | amp; 14 amp; 12 amp; 13 | amp; 4 amp; 3 amp; 3 | amp; Excellent amp; Excellent amp; Excellent |
| Team Total | amp; 49 | amp; 39 | amp; 10 | amp; 79.6% Complete |

## Team Performance Assessment:

All team members are performing at high levels with consistent productivity and quality output:

Priyanka Sharma: Excellent project coordination and stakeholder management. Strong leadership in resolving installation delays. Documentation and reporting exemplary.

Kayode Babalola: Outstanding work on energy audit and data analysis. Proactive in addressing sensor installation challenges. Strategic thinking evident in campaign planning.

Qianru Deng: Exceptional technical leadership on dashboard development. Skillful resolution of IT integration issues. Code quality and documentation excellent.

Team Collaboration: Highly effective cross-functional collaboration with open communication and mutual support.

# Risk Status Dashboard

| Risk | amp; Probability | amp; Impact | amp; Mitigation Status |
| --- | --- | --- | --- |
| Installation Delays | amp; High | amp; Medium | amp; Actively Mitigating |
| Low User Adoption | amp; Medium | amp; High | amp; Planning Phase |
| Technical Integration | amp; Low | amp; High | amp; Resolved ✅ |
| Budget Overrun | amp; Low | amp; Medium | amp; Monitoring |
| Timeline Slippage | amp; Low | amp; High | amp; Monitoring |

## Risk Management Summary:

Installation Delays: Active mitigation underway; increased crew size and revised schedule User Adoption: Comprehensive training and engagement strategy being developed Technical Integration: Successfully resolved through enhanced security measures Budget and Timeline: Both remain low-risk with adequate buffers in place

# Upcoming Milestones and Critical Dates

## Week of November 22-28:

November 22: Mid-project stakeholder review meeting November 25: Integration testing phase begins November 28: Dashboard prototype completion deadline

## Week of November 29 - December 5:

November 30: Training materials finalization

November 30: Educational campaign materials completion December 1: Final project delivery and official launch December 2: Post-launch review and lessons learned session

## Critical Path Activities:

- Complete sensor installation in remaining 7 buildings (deadline: Dec 1)

- Dashboard integration testing and bug fixes (Nov 25-30)

- User acceptance testing with 50-person test group (Nov 29-30)

- Final documentation and presentation preparation (Nov 29-Dec 1)

# Recommendations and Next Steps

Based on current project status and remaining timeline, the following recommendations are proposed:

## Immediate Actions (Next 7 Days):

- Accelerate Sensor Installation

Increase installation team to 4-person crew

Schedule weekend work if necessary to recover any remaining delays  Priority: Complete installations by November 28 to allow testing buffer

## Enhance User Adoption Strategy

Schedule minimum 3 hands-on training sessions in first week of December  Create video tutorials and quick-start guides for common tasks

Identify and recruit 10 "energy champions" across departments

Launch awareness campaign via campus communications channels

## Stakeholder Communication

Conduct mid-project review on November 22 to maintain stakeholder confidence  Provide weekly status updates to project supervisor

Prepare compelling demonstration for final presentation

## Contingency Planning

Maintain contingency fund for any last-minute issues

Develop backup plan for partial launch if critical issues emerge

Ensure all documentation current in case of team member unavailability

## Long-Term Considerations:

Document lessons learned for future similar projects Plan for post-launch support and system maintenance Identify opportunities for system expansion in Phase 2 Prepare sustainability plan for ongoing operations

# Project Statistics Summary

## Project Timeline:

Start Date: September 23, 2025

Current Date: November 20, 2025

End Date: December 1, 2025

Elapsed Time: 58 days (8.3 weeks)

Remaining Time: 11 days (1.6 weeks)

Overall Progress: 52% complete

## Team Performance:

Total Tasks: 49

Completed Tasks: 39 (79.6%)

In-Progress Tasks: 10 (20.4%)

Overdue Tasks: 0 (0%)

## Quality Metrics:

Defect Rate: 0.8% (well below 5% target)

Rework Rate: 2.1% (below 5% target)

## Stakeholder Satisfaction: 8.5/10

Team Morale: 8.7/10

Appendix: Acronyms and Definitions API: Application Programming Interface AWS: Amazon Web Services

HVAC: Heating, Ventilation, and Air Conditioning

IoT: Internet of Things

IT: Information Technology

kWh: Kilowatt-hour (unit of energy measurement)

MFA: Multi-factor Authentication REST: Representational State Transfer ROI: Return on Investment

TLS: Transport Layer Security

UI: User Interface

UAT: User Acceptance Testing

Document Classification: Internal Use Only Next Monthly Update: December 20, 2025 Prepared By: Priyanka Sharma, Project Manager

Reviewed By: Dr. Michael Chen, Project Supervisor