Project Charter

| PROJECT NAME |  | PROJECT MANAGERS | Team Name |
| --- | --- | --- | --- |
| Smart Campus Energy Management System |  | Kayode Babalola Qianru Deng Priyanka Sharma | Group001 |

PROJECT OVERVIEW

| PROBLEM OR ISSUE | Higher education campuses typically face high energy consumption with limited real-time monitoring and engagement to encourage sustainable practices among students and staff. |
| --- | --- |
| PURPOSE OF PROJECT | The purpose of this project is to build a comprehensive Smart Campus Energy Management System that audits energy consumption, implements sensor-based monitoring with dashboards, and runs an educational campaign to promote sustainability practices campus-wide. |
| BUSINESS CASE | This project will reduce campus energy costs by 10–15% through improved monitoring, automated controls, and better awareness, leading to an estimated payback period of less than two years. The initiative helps the university cut expenses, optimize resource use, and enhance its sustainability reputation while supporting future growth with lower operational costs. |
| GOALS / METRICS | - Complete campus-wide energy audit with actionable recommendations by Oct 31, 2025. - Deploy sensors covering at least 80% of campus facilities(Oct 26, 2025 to Nov 16, 2025). - Launch dashboards accessible to all stakeholders by Dec 1, 2025. - Engage 60% of the campus community through educational campaigns within 6 months. - Achieve 10% reduction in energy consumption within 1 year. - Track dashboard usage and educational participation monthly. |
| EXPECTED DELIVERABLES | - Energy Consumption Audit Report: A Comprehensive report detailing energy usage analysis and actionable recommendations for efficiency improvements. - Sensor Network Installation: Deployment and integration of sensors across campus to collect real-time energy consumption data. - Energy Monitoring Dashboard & Mobile App: User-friendly platforms accessible to students, staff, and facility managers for monitoring energy use and identifying saving opportunities. - Educational Campaign Materials: Workshops, posters, and digital media designed to engage the campus community in sustainable practices. - Project Management Documentation: Including the project communication plan, risk management plan, and overall project plan to ensure smooth execution and governance. |

PROJECT SCOPE

| WITHIN SCOPE | - Conduct comprehensive energy audits of all campus buildings and facilities. - Install sensors and develop dashboards for real-time energy monitoring and reporting. - Design and implement educational initiatives targeting students, faculty, and staff to promote sustainable energy practices. - Perform data analysis and generate actionable sustainability reports. - Provide training sessions and materials for dashboard users and campus community engagement. |
| --- | --- |
| OUTSIDE OF SCOPE | - Major infrastructure renovations or installation of renewable energy systems are excluded from this project. - Non-campus buildings or external facilities are not covered within the project scope. - Online training modules beyond the in-person educational campaign will not be developed or delivered. |

TENTATIVE SCHEDULE

| KEY MILESTONE (note these are examples below and you can choose to put in whatever you like from a Milestone basis) | START | FINISH |
| --- | --- | --- |
| Form Project Team / Preliminary Review / Scope | 9/23/2025 | 9/28/2025 |
| Finalize Project Plan / Charter / Kick Off | 10/1/2025 | 10/5/2025 |
| Define Phase (optional – choose what you like) | 10/5/2025 | 10/12/2025 |
| Planning Phase (optional) | 10/12/2025 | 10/26/2025 |
| Executing Phase (optional) | 10/26/2025 | 11/16/2025 |
| Project Summary Report and Close Out (optional) | 11/24/2025 | 12/1/2025 |

RESOURCES

| PROJECT TEAM | - Project Sponsor: Vice President of Operations & Facilities - Project Manager: One dedicated, full-time manager. - Core Team Members: Designated representatives from Facilities Management, IT Department, Finance Office, and Sustainability Office. |
| --- | --- |
| SUPPORT RESOURCES | - Financial Resources: An approved project budget for the procurement of hardware, software, and services. - Technical Support: The IT Department will provide necessary support for network infrastructure, data security, and server hosting. - Executive Support: The Project Sponsor will provide high-level advocacy to facilitate cross-departmental cooperation and remove obstacles. |
| SPECIAL NEEDS | - System Integration Access: Secure API/data interface access to existing campus systems, including the Building Management System (BMS) and class scheduling system. - Campus-Wide Access Rights: Authorization for the project team to install IoT sensors and equipment in all campus buildings and relevant locations. - Dedicated Analytics Platform: Deployment of a centralized, AI-capable data analytics platform for energy monitoring, prediction, and optimization. - Change Management Program: A dedicated plan and resources for managing organizational change, training facility staff, and promoting energy-saving awareness across the campus community. |

COSTS

| COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Labor | Energy Systems Engineer |  | $55/hr | 800hrs | $44,000 |
| Labor | Electrical Contractors (Installation) |  | $40/hr | 1,200hrs | $48,000 |
| Labor | Software Developers(IoT + Dashboard) |  | $60/hr | 1,000hrs | $60,000 |
| Labor | Data Scientists(Optimization & Analytics) |  | $60/hr | 600hrs | $36,000 |
| Labor | Project Manager |  | $65/hr | 400hrs | $26,000 |
| Supplies | IoT Sensors(Smart Meters, Motion, Temp) |  | $250/Unit | 150Units | $37,500 |
| Supplies | Networking Equipments(Gateways and Routers) |  | $1,500/Unit | 20Units | $30,000 |
| Supplies | Cloud Services(1year: Compute (VMs / App Backend) - USD 2,500, Storage & Analytics (Cloud Storage) - USD 1,500, Monitoring / Functions - USD 1,000) |  | $5,000/yr | 1 | $5,000 |
| Supplies | Control Software Licenses (Siemens Desigo CC: Base software license: $9,500, Integration with existing campus equipment through BACnet protocol: $4,000, Initial maintenance and support fees (approx. 10–15% of base license): $1,500) |  | $15,000 | 1 | $15,000 |
| Miscellaneous | Training and Workshop for Staff |  | $5,000 | 1 | $5,000 |
| Miscellaneous | Contingency(5% of Project) |  |  |  | $15,325 |
|  |  |  | TOTAL COSTS |  | $321,825 |

| TYPE OF BENEFIT (select your own and/or use these) | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Specific Cost Savings | Energy Efficiency: 15% reduction in utility bills. Campus annual electricity spend = $2M savings. |  |  |  | $300,000 |
| Enhanced Revenues | Ability to sell excess energy data insights to research grants. |  |  |  | $50,000 |
| Higher Productivity (Soft) | Smart Scheduling and Automation reduce manual monitoring(approx. 2 full time staff equivalent. |  |  |  | $140,000 |
| Improved Compliance | Meeting Provincial energy reporting and climate action requirements; avoid non-compliance penalties. |  |  |  | $25,000 |
| Better Decision Making | Real-Time dashboards, optimized resource allocation reduce unnecessary Overtime and energy. |  |  |  | $40,000 |
| Less Maintenance | Predictive Maintenance for IoT sensors reduces unplanned repairs. |  |  |  | $30,000 |
| Other Costs Avoided | Avoided cost of future system overhauls by modernizing now |  |  |  | $50,000 |
|  |  |  | TOTAL BENEFIT |  | $635,000 |

Financial Summary / Business Case

| Payback Period, NPV Analysis | $321,825(costs) / $635,000(annual benefits) ≈ 6months After the first year, the system pays for itself and generates ongoing savings. Long-term (5 years): ≈ $2.85M in net benefits after initial investment. |
| --- | --- |
| Non-financial Considerations | ROI is strong and payback is less than one year. |

RISKS, CONSTRAINTS, AND ASSUMPTIONS

| RISKS | - Potential delays or malfunctions in sensor hardware deployment could impact project timeline and data accuracy. - Risk of insufficient engagement or resistance from campus users reducing the effectiveness of dashboards and educational campaigns. - Technical integration challenges between sensors, data platforms, and dashboards. - Possible funding shortfalls limiting project scope or scale. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CONSTRAINTS | - The project budget limits the number and type of sensors that can be deployed initially. - Time constraints to complete installation and launch before target academic period. - Dependence on timely cooperation from campus facilities and IT departments for access and support. - Physical limitations in existing infrastructure for sensor installation. |  |  |  |  |  |
| ASSUMPTIONS | - Full cooperation and support from campus facilities management and IT teams will be available. - Users (students, staff, faculty) will actively engage with the dashboards and campaigns as intended. - Hardware and software components will function as expected without major technical failures. - Project funding and resources will be secured as planned. |  |  |  |  |  |

### REVISION SUMMARY

| Initial Submission | - Initial project charter submitted, including scope, schedule, and cost estimates. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Updated Submission | - Refined cost estimates (cloud + Siemens software). |  |  |  |  |  |
| Final Revision | - Added Solution Roadmap, Basecamp milestones, GitHub repo structure, and clarified assumptions. Ready for final review. |  |  |  |  |  |

| PREPARED BY |  | TITLE |  |  |  | DATE |
| --- | --- | --- | --- | --- | --- | --- |
| Kayode Babalola Qianru Deng Priyanka Sharma |  | Project Managers |  |  |  | September 25th, 2025 |